## Slide 1
INSTITUTIONAL DSS · LEVEL 3 ANALYTICS
PredictPay
Smart AR Analytics Dashboard
LSTM-Powered Decision Support System
for Accounts Receivable & Cash Flow Intelligence
12-Week
Project
$43,800
Budget
≥ 85%
Prediction Accuracy
20%
DSO Reduction

## Slide 2
THE PROBLEM
50%+
of B2B sales are overdue at any given time
10%
of every finance team's workday spent manually chasing unpaid invoices
Cash Flow Trapped
Finance teams are locked in manual follow-up cycles, inflating Days Sales Outstanding (DSO) and increasing credit risk across the portfolio.
No Predictive Intelligence
Xero and Sage provide historical aging reports only — no tool currently identifies which invoices will become delinquent before the due date.
Reactive, Not Proactive
Current processes trigger action after payment failure. The Board requires forward-looking signals that enable pre-emptive collection prioritization.

## Slide 3
PROJECT DEFINITION · STAR / SMART FRAMEWORK
S
SITUATION
Cash flow velocity is trapped in manual follow-up cycles, leading to inflated DSO and increased credit risk.
T
TASK
Initiate a 12-week project to build a predictive analytics dashboard that auto-categorizes risk and forecasts payment dates.
A
ACTION
Deploy AI-Augmented Scrum with 3 × 4-week sprints, serverless-first cloud architecture, and third-party accounting APIs.
R
RESULT
20% reduction in DSO and 60% automation of manual collection prioritization within first quarter of operations.
SMART PROJECT GOAL
Develop and transition a functional Smart AR Analytics product into production by June 2026
S
SPECIFIC
LSTM payment forecasting for Xero/Sage customers — classifying invoices as Early, On-time, or Late
M
MEASURABLE
Prediction accuracy ≥ 85% · 20% DSO reduction · 60% automation of manual collection tasks
A
ACHIEVABLE
12-week window, lean serverless squad, $43,800 minimalist budget
R
RELEVANT
Directly addresses 50%+ overdue AR backlog · 300–500% ROI in Year 1 via bad debt reduction
T
TIME-BOUND
Production cutover by Week 12 · Milestones at Weeks 4, 8, 12

## Slide 4
WORK BREAKDOWN STRUCTURE
1.0 PredictPay Management System (MVP)
1.1 API Integration
Infrastructure
1.1.1 Xero/Sage OAuth 2.0
Authentication Module
1.1.2 Automated Ledger
Ingestion Pipeline
(Invoices & Credits)
1.2 Predictive Core
Engine (Level 3)
1.2.1 Normalized Historical
Payment Dataset
(24-month history)
1.2.2 Validated LSTM
Payment Forecasting
Model
1.3 Decision Support
Interface (DSS)
1.3.1 Interactive Collection
Prioritization List
(By Risk Score)
1.3.2 Executive Cash Flow
Forecast
Visualizations
1.4 Governance &
Compliance Artifacts
1.4.1 GDPR-Compliant
Financial Data
Encryption Layer
1.4.2 Automated
Audit Trail
Logger

## Slide 5
12-WEEK AGILE ROADMAP
3 × 4-Week Sprints · Least Ceremony Overhead · Tracked via Burndown Charts & CFD
Sprint 1
Ingestion
Weeks 1–4
Data Readiness
Deliverable: Xero/Sage Connected Pipeline
Live API feed from accounting ecosystem with validated data flow
M1: Data Readiness Sign-off
Sprint 2
Analytics
Weeks 5–8
Predictive Alpha
Deliverable: Validated LSTM Model
Payment classification: Early / On-time / Late with confidence scores
M2: Predictive Alpha Validation
Sprint 3
Support
Weeks 9–12
Production Ready
Deliverable: Interactive AR Dashboard
30-day Shadow Mode + super-user training for credit control team
M3: Production Cutover Launch
Monitoring: Burndown Chart — sprint progress · CFD (Cumulative Flow Diagram) — WIP limits & bottleneck detection

## Slide 6
MULTI-DIMENSIONAL PROJECT REQUIREMENTS
Business
300–500% ROI in Year 1 through reduction of bad debt write-offs
Reduce Days Sales Outstanding (DSO) by 20% in first quarter
Solution — Functional
Payment classification: Early, On-time, or Late
Confidence intervals for each payment date forecast
Solution — Non-Functional
95–99% auto-matching accuracy on remittances
API synchronization latency under 5 seconds
Transition
Super-user training for the credit control team
30-day 'Shadow Mode' parallel launch vs. manual results
Quality
Data integrity check: no duplicate transactions posted to ledger
GDPR-compliant encryption for all financial data

## Slide 7
AGILE TEAM & ROLES
PO
Product Owner
Visionary: manages the Product Backlog and prioritizes features by Business Value (DSO reduction impact)
Stakeholder Liaison: translates CFO/Finance Director expectations into technical user stories
SM
Scrum Master
Facilitator: ensures Scrum principles are followed; time-boxes ceremonies to 8 hours per sprint
Guardian: protects developers from scope creep and removes API rate-limit impediments
DEV
ML Engineers &
Data Quants
Execution: determines model architecture and handles OAuth 2.0 API authentication
Quality Owner: adheres to Definition of Done — all model iterations are peer-reviewed and tested

## Slide 8
MINIMALIST BUDGET BREAKDOWN
Top-Down Estimate · Serverless-First GCP/Vertex AI · $43,800 Total
Infrastructure
Serverless GCP/Vertex AI Endpoints — Pay-as-you-go compute
$2,000
4.6%
Data Licensing
Accounting Software Sandbox Access — Xero/Sage API fees
$500
1.1%
Personnel
Junior Quant/Intern Team (Lean Squad) — model development & integration
$34,500
78.8%
Contingency (15%)
Known-Unknowns: API integration rework, data cleansing overruns
$6,800
15.5%
TOTAL · Minimalist Initiation Budget
$43,800

## Slide 9
EXPERIENCE CRITICAL EVALUATION
Key Learning: Data are first-class artifacts
70% of effort must be dedicated to data cleansing and normalization — 'Garbage In, Garbage Out' is particularly destructive in financial forecasting.
CHALLENGES & ALTERNATIVES
Integration Footprint Complexity
Xero and Sage use distinct rounding rules and tracking categories that differ from standard ML data models — requiring custom normalization pipelines.
Standalone CSV Upload Alternative
Considered to reduce API costs — rejected because it fails to deliver the real-time, proactive intelligence demanded by the Board.
Legacy Accounting Schema Mismatch
Historical ledger data arrives in formats incompatible with LSTM input tensors, requiring a dedicated ETL transformation layer.
DECISIONS ADOPTED
API-First Connectivity Strategy
Adopted real-time Xero/Sage OAuth 2.0 integration to ensure live, proactive signals rather than static snapshots.
Change Management Framework
Prioritized API-first design as a change management decision — ensuring board-level buy-in for real-time visibility.
Data-First Sprint Planning
Allocated 70% of Sprint 1 effort to ingestion, normalization, and deduplication before any model training begins.

## Slide 10
Transform AR from a Cost
Centre to a Competitive Edge
PredictPay — LSTM-Powered Smart AR Analytics DSS · June 2026 Production Cutover
≥ 85% Accuracy
20% DSO Reduction
$43,800 Budget
300-500% ROI
Prepared by PredictPay Project Team · 12-Week MVP Initiation Pitch · AI-Augmented Scrum